## send IT
PT. SEMARANG AUTOCOMP MANUFACTURING INDONESIA
FORM REQUEST IMPROVEMENT SYSTEM Term 84 s/d Term 94
No | DEP/SECT | PIC | Referensi | Nama Project | Fungsi | Merit | Demerit | TERM (Implementasi)
[8 empty] | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93
0 (Contoh) | PRD- KANBAN | YDS | Benchmark SUAI | Print Nameplate di Line | - Print nameplate di masing-masing Conveyor - Tracking Serial Nameplate - FIFO Proses | Q : Print NP sesuai dengan Plan PPC C : xxxx.xx / Bulan D : menghilangkan Proses distribusi NP S : M : Proses Print Mudah( Hanya dengan scan kanban) P : dapat mengurangi MP Supplay NP E : tidak ada NP Scrap | Q : C : Printer NP di semua Area D : S : M : P : E : | TERM (Implementasi) 83: 2023-09-01
GA - LOCAL PURCHASE
1 | PGA-GA | FYH | Konsep SAMI | SUMMARY PERMINTAAN BARANG KE SUPPLIER | Mempermudah pencarian barang ke supplier | Q : Local purchase dapat menjangkau seluruh vendor saat membutuhkan barang C : - D : Mengurangi waktu untuk mengirimkan vendor satu-persatu S : M : Mempermudah Local Purchase menjangkau seluruh vendor P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-09-01
2 | PGA-GA | FYH | Konsep SAMI | PERSETUJUAN PO (PURCHASE ORDER) OLEH ATASAN | - Pengajuan approval tanda tangan memerlukan waktu yang lama | Q : Proses pengajuan approval purchase order menggunakan sistem C : D : proses pengajuan approval lebih cepat dan mengurangi waktu scan S : M : Mempermudah jalannya proses purchase order P : Waktu yang digunakan untuk scan dan pengajuan approval dapat digunakan untuk pekerjaan lain E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-10-01
3 | PGA-GA | FYH | Konsep SAMI | PO ADA LINK DOWNLOAD KONTRAK | - Integrasi kontrak antara legal dan local purchase | Q : Request dan hasil kontrak dapat diakses langsung oleh local purchase dan legal C : D : Request dan hasil kontrak dapat lebih cepat diakses dan diteruskan ke vendor S : M : Local purchase dan legal lebih mudah berkomunikasi mengenai kontrak P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-09-01
4 | PGA-GA | FYH | Konsep SAMI | PEMBUATAN DOKUMEN MASUK TANPA BC 4.0 | Local purchase tidak perlu melakukan pendataan dan input manual | Q : Data barang dan invoice langsung masuk ke sistem C : D : Pendataan barang dan invoice lebih cepat karena langsung ke sistem S : M : Local purchase lebih mudah dalam pembuatan dokumen dan penerimaan barang P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-10-01
5 | PGA-GA | FYH | Konsep SAMI | PROSES KEDATANGAN BARANG | Local purchase tidak perlu melakukan pendataan dan input manual | Q : Barang yang datang dapat terinput otomatis C : D : Input data kedatangan barang lebih cepat S : M : Local purchase merasa lebih mudah dalam pendataan kedatangan barang karena dalam purchase order terdapat barcode dan bisa langsung discan masuk ke sistem P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-09-01
6 | PGA-GA | FYH | Konsep SAMI | KONFIRMASI USER SAAT DISTRIBUSI BARANG | User mendapatkan notifikasi waktu kedatangan barang | Q : User mendapatkan info langsung kapan barang yang dipesan datang C : D : Local purchase tidak perlu menghubungi user satu persatu S : M : Proses konfirmasi user lebih mudah karena user mendapatkan notifikasi otomatis P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-09-01
GA - MANAGEMENT BUILDING
7 | PGA-GA | STI | Konsep SAMI | Management Building | - Data terintegrasi - Penyimpanan data lebih terorganisir | Q : Kondisi building lebih terkontrol C : Mengurangi printout kertas setiap bulan D : Mengurangi proses penggantian checksheet setiap bulan, atasan dapat mengontrol pengisian dari pc masing-masing S : M : Proses pengisian di lapangan dapat langsung terlihat di komputer atasan P : Mengurangi proses pencatatan kerusakan manual E : | Q : C : scanner tiap pic 1 D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
8 | PGA-GA | STI | Konsep SAMI | Control external worker security dan cleaning service | Kinerja CS dan security lebih terkontrol dan report lebih cepat | Q : Kinerja sesuai dengan keinginan user C : D : Mengurangi lama waktu koordinasi S : M : Mempermudah komunikasi P : Pekerjaan dapat terfollup lebih cepat E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-09-01
GA - LEGAL
9 | PGA-GA | STI | Konsep SAMI | Manajemen peraturan perundangan | - Regulasi terdistribusi otomatis | Q : Regulasi dapat otomatis terkirim ke user C : D : Mengurangi pengiriman manual dengan email S : M : Mempermudah distribusi regulasi ke user P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-07-01
10 | PGA-GA | STI | Konsep SAMI | Manajemen kontrak kerjasama | - Kontrak dapat terakses oleh legal dan pic kontrak | Q : Notifikasi yang berkaitan dengan kontrak dapat otomatis didapatkan pic kontrak C : D : Legal tidak perlu reminder berkali-kali ke pic kontrak S : M : Mempermudah legal tentang status kontrak P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-07-01
11 | PGA-GA | STI | Konsep SAMI | Manajemen perijinan, laporan, sertifikasi | - Perijinan dapat terakses oleh legal dan pic kontrak | Q : Notifikasi yang berkaitan dengan perijinan dapat otomatis didapatkan pic C : D : Legal tidak perlu reminder berkali-kali ke pic perijinan S : M : Mempermudah legal tentang status perijinan P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-07-01
12 | PGA-GA | STI | Konsep SAMI | Manajemen CSR | - Digitalisasi kontrol CSR | Q : Pelaksanaan lebih terjadwal C : D : S : M : Proses persiapan CSR dan pelaporan lebih mudah P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-07-01
GA - GENERAL SUPPORT
13 | PGA-GA | FYH | Konsep SAMI | Evaluasi Katering | - Evaluasi catering harian | Q : Evaluasi catering lebih menjangkau seluruh karyawan C : D : Mengurangi waktu MP GA evaluasi catering manual S : M : Mempermudah evaluasi catering P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
14 | PGA-GA | FYH | Konsep SAMI | Surat jalan driver | Surat jalan / Instruksi & Notifikasi kegiatan driver di akses online melalui Smart Phone ataupun PC dan dapat diterima oleh driver melalui Smart Phone Ada button khusus yang diklik oleh security ketika driver out dan in yang kemudian secara otomatis muncul jam dan button untuk input nama security yang bertugas | Q : Driver langsung ke security daat ada instruksi atau notifikasi jalan C : D : Mengurangi waktu untuk driver ke resepsionis S : M : Proses driver keluar lebih mudah dan singkat P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
15 | PGA-GA | FYH | Konsep SAMI | Notifikasi kegiatan dining room | Request di dining room lebih mudah | Q : Request menu, kegiatan makan, langsung diakses dari dining room C : D : Konfirmasi menu atau kegiatan makan tidak perlu ke resepsionis S : M : Resepsionis merasa lebih terbantu dalam kegiatan tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
GA - UTILITY
16 | PGA-GA | FYH | Konsep SAMI | PATROLI HARIAN GENSET | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli genset melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
17 | PGA-GA | FYH | Konsep SAMI | PATROLI HARIAN KOMPRESSOR | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli kompressor melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
18 | PGA-GA | FYH | Konsep SAMI | PATROLI HARIAN AHU | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli AHU melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
19 | PGA-GA | FYH | Konsep SAMI | PATROLI HARIAN AUTODRAIN | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli autodrain melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
20 | PGA-GA | FYH | Konsep SAMI | PATROLI HARIAN PUMP ROOM DAN HYDRANT | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli pump room dan hydrant melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
21 | PGA-GA | FYH | Konsep SAMI | PATROLI MINGGUAN TRAFO | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli trafo melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
22 | PGA-GA | FYH | Konsep SAMI | PATROLI MINGGUAN PANEL LISTRIK | Hasil patroli dapat langsung dimonitor di sistem | Q : Patroli panel listrik melalui scanner barcode dan dapat langsung masuk ke sistem C : D : Utility tidak perlu input data hasil patrol manual S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
23 | PGA-GA | FYH | Konsep SAMI | PROSES IN - OUT MATERIAL UTILITY | Proses in-out barang dapat lebih terkontrol | Q : Proses in-out dan stok barang terkontrol C : D : Utility lebih cepat mengetahui stok barang di gudang S : M : Utility merasa terbantu dengan sistem tersebut P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
24 | PGA-GA | FYH | Konsep SAMI | PROSES BULANAN PENGECEKAN KIPAS ANGIN | Tanggal pemasangan dan lifetime kipas terecord | Q : Data kipas dan lifetime kipas terecord C : D : Utility lebih cepat mengetahui data kipas S : M : Kontrol kipas lebih mudah P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
25 | PGA-GA | FYH | Konsep SAMI | RECORD HISTORI MESIN | Pengecekan, pendataan, pelaporan masih manual | Q : History mesin terecord C : D : Utility lebih cepat mengetahui histori tiap-tiap mesin S : M : History mesin lebih mudah dimonitor P : E : | Q : C : D : S : M : P : E : | TERM (Implementasi) 84: 2024-08-01
Note on D7: Contoh : - Benchmark ke Affiliate - Bechmark PT xxxx - Youtube lik …..... - Internet link …... - Konsep SAMI
Note on G7: Boleh diisi saat Meeting Opening Project
Note on H7: Boleh Diisi saat Meeting Opening Project

## Target
A. DAFTAR PLAN DIGITALISASI GA
NO. | JUDUL PROJECT | SECT.
1 | Appointment Tamu Jalur Lobby | GA - GS
2 | Appointment Tamu Jalur Security | GA - GS
3 | Evaluasi Katering Online Oleh Karyawan | GA - GS
4 | SPD Online (Perjalanan Dinas) | GA - GS
5 | Perintah Kerja Driver Online | GA - GS
6 | Data & ID Card External Worker Online | GA - GS
7 | Serah Terima Barang LP | GA - LP
B. RELEASE DOK. GA
NO. | JUDUL PROJECT | SECT. | JENIS | NO. DOK | TGL RELEASE | KAIZEN
1 | Penanganan Kondisi Abnormal pada Lampu | GA - UTY | OSI | OSI/GA-UTY-025 | 2024-04-05
2 | Patroli Harian Lampu | GA - UTY | OSI | OSI/GA-UTY-026 | 2024-05-07
3 | Patroli Harian Pengecekkan Lampu | GA - UTY | FORM | 020/PGA/GA-UTY/FORM/PHPL | 2024-04-25
4 | Checksheet Abnormal Lampu | GA - UTY | FORM | 021/PGA/GA-UTY/FORM/CAL | 2024-04-29

## Summary
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | SUMMARY PROGRES DIGITALISASI GA | [58 empty] | Plan
Enter Company Name in cell B2. | PT SEMARANG AUTOCOMP MANUFACTURING INDONESIA | [58 empty] | Actual
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: |  |  | 2024-05-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  |  | 1 |  |  |  | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2024-05-13 to 2024-07-07
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO |  | PROGRESS | START | END | Week End | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | DIGITALISASI GA |  |  | 70% | 2024-05-13 | 2024-06-30 |  | 49
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | APPOINTMENT (Jalur Lobby) | SJM | Plan | 100% | 2024-05-13 | 2024-05-27 | 6 | 9
|  |  | Act | 50% | 2024-05-13 | 2024-05-12
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | APPOINTMENT (Jalur Security |  | Plan |  | 2024-05-13 | 2024-06-30 | 19 | 30
|  |  | Act | 30% |  | -1
| EVALUASI KATERING ONLINE |  | Plan | 100% | 2024-05-20 | 2024-05-19
|  |  | Act |  |  | -1
|  |  | Plan |  | 2024-05-27 | 2024-05-26
|  |  | Act |  |  | -1
|  |  | Plan |  | 2024-05-13 | 2024-05-12
|  |  | Act |  |  | -1
|  |  | Plan |  | 2024-06-01 | 2024-05-31
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on E6: Author: Isi Status Progres terakhir pada baris Act
Note on H6: Author: Isi Jumlah hari tidak melakukan Task dari Start Date
Note on I6: Author: Isi Jumlah hari melakukan Task dari Start Date

## Appointment
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Appointment | [58 empty] | Plan
Enter Company Name in cell B2. | PT SEMARANG AUTOCOMP MANUFACTURING INDONESIA | [58 empty] | Actual
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: |  |  | 2024-05-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  |  | 1 |  |  |  | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2024-05-13 to 2024-07-07
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO |  | PROGRESS | START | END | Week End | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Tamu (Jalur Lobby) |  |  | 44% | 2024-05-13 | 2024-06-14 |  | 33
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Menghilangkan List Tamu dari Tablet | SJM | Plan |  | 2024-05-13 | 2024-05-15 |  | 3
|  |  | Act | 80% | 2024-05-13 | 2024-05-13 |  | 1
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Tambahkan Pilihan Others / Supplier di Web Admin | SJM | Plan |  | 2024-05-13 | 2024-05-20 | 3 | 5
|  |  | Act | 50% |  | -1
| Buat Standarisasi | Renny | Plan |  | 2024-05-20 | 2024-05-26 | 2 | 5
|  |  | Act | 10% |  | -1
| Sosialisasi ke ALL Dept | Renny | Plan | % | 2024-05-27 | 2024-05-28 |  | 2
|  |  | Act | 0% |  | -1
| Kelengkapan | Renny | Plan |  | 2024-05-13 | 2024-05-26 | 4 | 10
|  |  | Act | 80% |  | -1
| Implementasi | Renny | Plan |  | 2024-06-01 | 2024-06-14 |  | 14
|  |  | Act |  |  | 1900-01-04 |  | 6
| Appointment (Jalur Security) |  |  | #DIV/0! | 0 | -1 |  | 0
| Register Semua Supplier | GA | Plan |  |  | -1
|  |  | Act |  |  | -1
| Kelengkapan | GA | Plan |  |  | -1
|  |  | Act |  |  | -1
| Trial Ulang |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
|  |  | Plan |  |  | -1
|  |  | Act |  |  | -1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on E6: Author: Isi Status Progres terakhir pada baris Act
Note on H6: Author: Isi Jumlah hari tidak melakukan Task dari Start Date
Note on I6: Author: Isi Jumlah hari melakukan Task dari Start Date